## Sheet1
Appendix 3
Probability |  |  |  | Impact |  |  | Risk Rating
1 - Improbable (10%) |  |  |  | 1 - Insignificant |  |  | 0-5 - Very Low
2 - Unlikely (30%) |  |  |  | 2 - Marginal |  |  | 6-9 - Low
3 - As likely as not (50%) |  |  |  | 3 - Serious |  |  | 10-14 - Medium
4 - Probable (70%) |  |  |  | 4 - Critical |  |  | 15-19 - High
5 - Highly Probable (90%) |  |  |  | 5 - Catastrophe |  |  | 20-25 - Very High
Risk |  |  |  |  | Mitigation
|  |  |  | Pre |  |  |  | Post
|  |  |  | mitigation |  |  |  | mitigation
Item |  | Prob | Impact | Risk |  | Prob |  | Risk
Ref | Risk | L1-5H | L1-5H | Rating | Target/Control Measure | L1-5H | Impact | Rating
Governance
| Board of Trustees lacking requisite skill and experience to oversee and guide the organisation | 3 | 4 | 12 | Define Trustee requirements clearly; consult stakeholders; advertise widely; engage external support for recruitment process. Opportunity to defer start date if necessary
| Inadequate infrastructure to support trustees (regular MI; meeting routines) | 2 | 3 | 6 | Ensure management understands clearly and prioritises delivery of relevant, timely and accurate information to Trustees, within framework of regular meetings
Management/staffing
| Failure to recruit/retain satisfactory Theatre Manager and other key staff | 3 | 4 | 12 | Define role and candidate qualities clearly, referencing/benchmarking to appropriate comparator organisation where helpful. Set appropriate salary. Conduct thorough recruitment process
| Management/adminstration roles insufficient to manage expected workload | 2 | 3 | 6 | Benchmark budgeted activity levels and staff provision against relevant comparator organisations; map job descriptions against detailed operational plans. Monitor closely during intial phase after opening.
| Failure to recruit/retain sufficient volunteers | 2 | 3 | 6 | Plan sufficient lead time for volunteer recruitment and training. Design rolling recruitment process to bolster and replenish volunteer base.
Artistic
| Poor quality programme; incoherent artistic policy | 2 | 4 | 8 | Recruit Theatre Manager and Trustees with experience of managing/programming performing arts venue. Trustees to define guiding principles of artistic policy/aspiration
Operational
| Inadequate space to accommodate staff | 3 | 3 | 9 | review accommodation/layout plans carefully alongside staffing plan. Consider optimal scheduling of part-time working to minimise space needs
| Failure to manage effective get in/out; show set-up; modifying auditorium for different events | 2 | 4 | 8 | Recruit experienced Technical Manager and ensure close collaboration with Theatre Manager for scheduling stage time and events
Economic/market
| Downturn in demand for performance attendance, and/or demand for private events | 3 | 4 | 12 | adopt rolling financial forecasting, updating actual box office and private hires performance at the earliest opportunity; maintain maximum budget flexibility (in booking of shows and staff recruitment) in order to be able to react to adverse performance accordingly. adopt prudent reserves policy in order to build financial buffer (to allow flexibility to restrucure operation in response to adverse economic circumstances)
PR/public profile
| Beehive Centre not positively regarded; failing to meet expectations | 2 | 3 | 6 | design strong PR plan for venue launch; monitor media profile closely
Financial
| Insufficient cashflow and lack of access to liquid funds | 3 | 4 | 12 | adopt robust cash planning capability and monitor closely. Consider back-up financing facility to address short-term cash deficits
| Risk that target financial result is not achieved | 3 | 4 | 12 | ensure financial management information available regularly and accurately; ensure necessary flexibility in budget planning to allow planning response to underperformance
| Inadequate regular financial reporting | 2 | 4 | 8 | Define financial reporting needs and assign responsibilities clearly
| Fraud/misappropriation of funds | 2 | 4 | 8 | design and implement robust control processes for payment authorisation and pre-approval of purchase commitments. Trustees to oversee internal control infrastructure
| Financial management & planning resource not appropriate or sufficient | 2 | 4 | 8 | ensure alignment between operational/administrative requirements and staff responsibilities
Political
| Failure to maintain subsidy at required level makes Trust un-viable. | 2 | 5 | 10 | Gain political understanding and support for the subsidy. Enter into long-term agreement with Trust for peppercorn rent and subsidy
Statutory
| Failure to comply with relevant stautory requirements, risking reputational damage and/or financial penalties e.g. for hygeiene standards, safe working practices, employment practices, statutory returns for HMRC, Companies House and Charity Commission purposes | 2 | 4 | 8 | ensure responsibilty assigned for all elements of statutory compliance and structure implemented to enable regular review and monitoring at Trustee Board level.